## Slide 1
FINAL PRESENTATION
18 December 2025
Group 25 - SkySytem

## Slide 2
SUMMARY
TEAM
RELEASE PLAN
VISION AND SCOPE
BACKLOG ITEMS
METRICS
KPI
LESSONS LEARNED
1
2
3
4
5
6
7
Presented by → Beatriz Marques

## Slide 3
1. TEAM

## Slide 4
TEAM MEMBERS
Group 25
Link: repositorio_gitlab
Presented by → Beatriz Marques
Pedro Amorim
Tiago Oliveira
Beatriz Marques
António Correia
José Moreira
2022157609
2023129464
2022137934
2022141330
2022132718
2022157609@isec.pt
2023129464@isec.pt
2022137934@isec.pt
2022141330@isec.pt
2022132718@isec.pt
@thyi8
@beatrizsmrqs
@mAd-5864
@AntonioCorreia17
@jjMoreira

## Slide 5
TEAM ROLES
Group 25
Link: repositorio_gitlab
Presented by → Beatriz Marques
Pedro Amorim
Tiago Oliveira
Beatriz Marques
António Correia
José Moreira
S0 →
Scrum Master
Dev
Product Owner
Dev
QA Engineer
S1 →
S2 →
S3 →
S4 →
Scrum Master
Dev
Dev
Product Owner
QA Engineer
Scrum Master
Dev
Dev
QA Engineer
Product Owner
Scrum Master
Product Owner
QA Engineer
Dev
Dev
Dev
Dev
Product Owner
QA Engineer
Scrum Master

## Slide 6
2. VISION AND SCOPE

## Slide 7
VISION AND SCOPE
  No Inspiration → Focuses only on logistics (dates/prices), ignoring discovery.
  One-Size-Fits-All → Ignores user history and preferences.
  Tedious → Planning feels like a chore, not an experience.
Presented by → António Correia
THE PROBLEM : Generic & Transactional
THE VISION: Your
Intelligent Travel Companion
  Personalized → Understands your unique "Travel Personality".
  Proactive → Suggests destinations before you even search.
  Inspiring → Transforms booking into an engaging journey.
THE SCOPE: Flight &
Discovery
  Focus → Flight Reservations & Destination Discovery only.
  Core Tech → AI "Inspire Me" Engine & Smart Flight Search.
  Exclusions → No hotels or ground transportation for now.

## Slide 8
3. RELEASE PLAN

## Slide 9
RELEASE PLAN
Release 1 MVP
Product Goal → Manage user preferences, suggest destinations based on user preferences, ability to search and filter flights​
Date → 20/Nov
Release → v1.0
Plan
US2, US4, US6, US7, US8​
Story Points → 1 XL + 1 L + 1 M + 2 S​
Presented by → Tiago Oliveira
Release 2 Final
Product Goal →
  Introduce the capability for users to save desired flights Favorites from the search results
  Integrate a basic mechanism to provide
notifications related to these saved flights
  Deliver the new UI enhancements
  Integrate User Account
Date → 18/Dec
Release → v2.0
Plan
US1+US3+US9
Story Points → 1 L + 2 M

## Slide 10
4. BACKLOG ITEMS

## Slide 11
BACKLOG ITEMS
Sprint 1
  US4: New User Onboarding Quiz (M)
  US2: User Travel Preferences (S)
  US6: “Inspire Me” Destination Suggestions (XL)*
  US7: Basic Flight Search (L)*
Sprint 2
  US6: “Inspire Me” Destination Suggestions (XL)
  US7: Basic Flight Search (L)
  US8: Filter and Sort Flight Results (S)
Sprint 3
  US1: New User Registration and Login (L)
  US3: User Trip Dashboard
Sprint 4
  US9 Flight Status Notification (M)
Presented by → José Moreira

## Slide 12
5. METRICS

## Slide 13
METRICS
PLANNED
Presented by → José Moreira
  User Stories : 9
  Time effort
    Product Owner: 16h
    Scrum Master: 12h
    QA Engineer: 14h
    Team: 120
  User Stories : 8
  Time effort
    Product Owner: 13h
    Scrum Master: 13h
    QA Engineer: 18h
    Team: 160
DONE

## Slide 14
METRICS
Presented by → José Moreira
Sprint 0: 46h → 9 200€
Sprint 1: 38h → 7 600€
Sprint 2: 40h → 8 000€
Sprint 3: 40h → 8 000€
Sprint 4: 40h → 8 000€
TOTAL COST → 40 800€
PRODUCTION COST

## Slide 15
METRICS
Presented by → Pedro Amorim
PRODUCTIVITY
We applied the Fibonaci sequence to the T-Shirt sizes to convert them to Story Points.
(Task = 1 SP | S = 2 SP | M = 3 SP | L = 5 SP | XL = 13 SP )
  Planned SP: 69
  Delivered SP: 60
  Average Sprint Velocity: 12

## Slide 16
METRICS
EFFORT
Presented by → Pedro Amorim

## Slide 17
METRICS
EFFORT
Presented by → Pedro Amorim

## Slide 18
METRICS
QUALITY
Presented by → António Correia

## Slide 19
6. KPI

## Slide 20
SPRINT
GOALS
SPRINT GOAL SUCCESS RATE MEASURED BY USER STORIES
Presented by → José Moreira
After the initial sprint we managed to always achieve or surpass the sprint goal

## Slide 21
CUSTOMER LOYALTY
Presented by → José Moreira
We measured the customer loyalty using a net promoter score with answers received in surveys to potential users.
TOTAL ANSWERS
47

## Slide 22
7. LESSONS LEARNED

## Slide 23
LESSONS LEARNED
What lessons do you leave for future projects?
  José Moreira: We realized that adapting to different working styles and bridging communication gaps were our biggest hurdles. However, we discovered that establishing a well-defined workflow was the key to overcoming these friction points, providing the structure needed to align the team and streamline collaboration.
  Pedro Amorim: This project taught me that 'flexibility' requires a solid foundation. Our team initially struggled with the rapid pace of change and varying communication habits, but we found our stride by consolidating our Scrum framework. Establishing this consistent workflow was the key to eliminate team friction.
Presented by → Tiago Oliveira

## Slide 24
LESSONS LEARNED
What lessons do you leave for future projects?
  Beatriz Marques: I learned that effective planning goes beyond just listing features; it requires realistic estimation and risk management. We initially struggled with overarching some user stories and blocking external dependencies like API limits. However, we found that decomposing complex features into granular tasks and implementing fallback strategies were the keys to balancing the workload and ensuring continuous delivery without bottlenecks.
  Tiago Oliveira: The start of the project was characterized by a steep learning curve. We faced initial difficulties with team organization and a lack of experience with essential tools like GitLab. However, through a collective effort and the establishment of a rigorous workflow, we successfully overcame these barriers. This challenge evolved into an opportunity for growth, allowing us to master new tools and strengthen our collaboration.
Presented by → Tiago Oliveira

## Slide 25
THANK YOU !!